## 8-Week Roadmap
Cloud-Menu: 8-Week Agile Implementation Roadmap
Kickoff date (Monday of Week 1): |  | 2026-11-02 | INPUT (assumed date, change to the real kickoff). Start/End dates below recalculate. Check festive-season (December) trading peaks when fixing go-live.
Sprint | Start wk | End wk | Start (Mon) | End (Fri) | Workstream | Deliverable / milestone | Stories | Owner role | Exit criterion
Setup | 0 | 0 | 2026-10-26 | 2026-10-30 | Product | Aggregator shortlist and sandbox access requested; venue interviews (5-8 per persona); counts of candidate venues | - | Founder / PO | Aggregator chosen; interview insights fed into backlog
Setup | 0 | 0 | 2026-10-26 | 2026-10-30 | Engineering | Repo and monorepo, CI/CD with Lighthouse budget, Terraform base, staging environment, observability skeleton | - | Tech Lead | Hello-world deploys to staging through CI
Setup | 0 | 0 | 2026-10-26 | 2026-10-30 | Design | Mobile-first design system, wireframes for Screens A-C, EN/SW copy deck | - | Designer | Design review signed by PO
S1 | 1 | 2 | 2026-11-02 | 2026-11-13 | Platform | DB schema migrations, staff auth with roles, venue/table models, QR generation and signed tokens | US-506, US-602 | Backend | QR PDF printed and scanned on 3 device types
S1 | 1 | 2 | 2026-11-02 | 2026-11-13 | Guest app | Session init and participants, menu browse, modifiers, cart, order submit (idempotent) | US-101, US-102, US-201, US-202, US-203, US-204 | Full-stack | Scan QR, order, order stored (staging)
S1 | 1 | 2 | 2026-11-02 | 2026-11-13 | Venue admin | Menu CRUD with image optimisation and CSV import | US-601 | Full-stack | Pilot menu loaded in under 1 hour
S1 | 1 | 2 | 2026-11-02 | 2026-11-13 | Performance | PWA shell, service worker, bundle budget enforced in CI | US-701 | Front-end | LCP at most 4.0 s on Fast 3G profile
S1 | 2 | 2 | 2026-11-09 | 2026-11-13 | Milestone | M1: Ordering core demoable in staging |  | Team | Sprint 1 review: ticket data visible via API
S2 | 3 | 4 | 2026-11-16 | 2026-11-27 | Staff app | KDS ticket queue and state changes, waiter dashboard (tables, balances), real-time channels (SSE and WebSocket) | US-501, US-502, US-504 | Full-stack | Order-to-ticket p95 at most 2 s in staging
S2 | 3 | 4 | 2026-11-16 | 2026-11-27 | Billing | Bill view, equal split, itemized split with claims, split lock with expiry and concurrency control | US-301, US-302, US-303, US-305 | Backend + Front-end | All Gherkin split scenarios automated and green
S2 | 3 | 4 | 2026-11-16 | 2026-11-27 | Payments | Aggregator integration in sandbox: push initiation, idempotency, payment states | US-401 | Backend | Sandbox payment succeeds for each wallet
S2 | 4 | 4 | 2026-11-23 | 2026-11-27 | Milestone | M2: Split and pay in sandbox, end to end |  | Team | Demo: 3 guests split and pay in sandbox, ticket on KDS
S3 | 5 | 6 | 2026-11-30 | 2026-12-11 | Payments | Webhooks (signature, dedupe, async processing), failure and retry flows, reconciliation job, late-success handling | US-402, US-403, US-404, US-407 | Backend | Chaos test: dropped/duplicated callbacks reconcile correctly
S3 | 5 | 6 | 2026-11-30 | 2026-12-11 | Guest app | Order status tracking, sold-out sync, digital receipts | US-205, US-206, US-405 | Full-stack | Receipt generated for every successful payment
S3 | 5 | 6 | 2026-11-30 | 2026-12-11 | Resilience | Reconnect and resync, offline banners, polling fallback; rate limiting and security hardening; metrics and alerts | US-505, US-702, US-703 | Tech Lead | Network-drop test passes; alerts fire in drill
S3 | 5 | 6 | 2026-11-30 | 2026-12-11 | Quality | Load test (target 9,000 connections), live-money test with small amounts, pen-test checklist, device matrix pass | - | QA | No open critical/high defects
S3 | 6 | 6 | 2026-12-07 | 2026-12-11 | Milestone | M3: Pilot readiness review (go/no-go for beta) |  | Founder + Tech Lead | Readiness checklist complete
S4 | 7 | 8 | 2026-12-14 | 2026-12-25 | Operations | Session lifecycle, cash payment recording, station routing, call waiter, tipping | US-103, US-104, US-406, US-503, US-207, US-306 | Full-stack | Waiter can resolve unpaid-share cases without engineering
S4 | 7 | 8 | 2026-12-14 | 2026-12-25 | Venue admin | Daily sales summary and export, venue sign-up and subscription, shared items | US-603, US-604, US-304 | Full-stack | Manager reconciles a day in under 10 minutes
S4 | 7 | 8 | 2026-12-14 | 2026-12-25 | Launch | Pilot onboarding playbook, venue training (30 min), QR sticker installation, support rota for first weekends, feedback loop | - | Founder / Support | First 5-10 pilot venues live
S4 | 8 | 8 | 2026-12-21 | 2026-12-25 | Milestone | M4: MVP beta launch |  | Team | Pilot KPIs dashboard live; hypercare started
Notes
- Week 0 is pre-sprint setup (about one week before Week 1); Start date for week 0 falls one week before kickoff.
- Sprint cadence: planning (Mon), daily stand-up, mid-sprint refinement, review and retro (Fri of week 2). Definition of Ready/Done in 02_Product_Backlog.xlsx.
- Scope flex: S4 holds Should/Could stories; cut them first if S1-S3 slip. Must-have path is complete at the end of S3.
- Story IDs refer to the Backlog sheet in 02_Product_Backlog.xlsx.
Formulas:
Start (Mon) = C2+([Start wk]-1)*7
End (Fri) = C2+([End wk]-1)*7+4

## Sprint Goals
Sprint | Weeks | Sprint goal | Demo at review | Key risks to watch
S1 | 1-2 | A guest can scan a table QR, browse a fast menu, customise and submit an order that is stored and visible via API. | Live scan on a mid-range phone over 4G; order appears in the database/API; QR sticker sheet printed. | R03 performance on weak networks; R16 team capacity
S2 | 3-4 | Staff see tickets in real time, guests can split the bill and start a sandbox mobile money payment. | Three phones: order, KDS ticket, split, sandbox payment. | R01 callbacks; R02 aggregator sandbox quality; R08 split concurrency
S3 | 5-6 | Payments are production-grade (webhooks, retries, reconciliation) and the system survives network drops. | Fault-injection demo: kill callbacks, drop Wi-Fi, replay events; live small-amount payments. | R01, R04, R10 duplicate payments
S4 | 7-8 | Pilot venues are live with training, support and reporting; beta feedback loop running. | First real venue service; KPI dashboard. | R06 adoption; R12 support load; R15 festive-season timing

## Risk Matrix
Risk Assessment & Mitigation Matrix
Probability and Impact are 1-5 (blue cells are editable inputs). Score = P x I. Rating: Critical >= 15, High 10-14, Medium 5-9, Low < 5.
ID | Category | Risk | Cause / trigger | P (1-5) | I (1-5) | Score | Rating | Mitigation (preventive) | Contingency (if it happens) | Owner | Early-warning indicator | Status
R01 | Technical | Failed or delayed payment callbacks leave paid shares showing unpaid | Aggregator outage, network failure, our endpoint down, bad signature handling | 4 | 5 | 20 | Critical | Persist raw webhook before processing; respond 200 fast; async worker; reconciliation polling for PENDING > 3 min; idempotent transitions; alert on pending age > 10 min; synthetic callback tests in staging. | Waiter dashboard shows "verify payment" with provider reference lookup; manual mark-paid with audit log; daily reconciliation report. | Tech Lead | Pending payments older than 5 min; webhook lag p95 | Open
R02 | Technical | Mobile money push prompts not delivered or aggregator downtime | Provider USSD/STK issues, aggregator maintenance, network congestion on peak nights | 3 | 5 | 15 | Critical | Contract SLA and status page; retry with backoff and resend-prompt button; alternate provider path in architecture (adapter interface); health probes and alerting. | Offer cash recorded by waiter; announce degraded mode on staff screens; switch to backup aggregator if contracted. | Tech Lead / Founder | Initiation failure rate above 5% in 10 min | Open
R03 | Technical | Slow loads and timeouts on 3G/4G and mid-range phones lead to abandonment | Heavy bundles, large images, high latency to hosting region, congested venue networks | 4 | 4 | 16 | Critical | Performance budget in CI (JS <= 150 KB gz, LCP targets); image variants via CDN; service worker caching; region latency test in Week 1; skeleton screens; menu cache with ETag. | Lite mode (text-only menu); move hosting region or add CDN rules; hotfix bundle regressions. | Front-end Lead | RUM LCP p75 above budget; scan-to-menu failures | Open
R04 | Operational | Venue Wi-Fi drops make KDS/waiter views stale (offline kitchen state) | Weak routers, shared Wi-Fi, power cuts | 4 | 4 | 16 | Critical | Auto-reconnect with seq resync; offline banner; polling fallback; staff devices can use mobile data hotspot; recommend dedicated router in onboarding checklist; optional printed ticket fallback (post-MVP). | Revert to verbal/paper ordering for the affected shift; staff manually refresh; support call-out. | Support Lead | Staff-device disconnect rate; reconnect time p95 | Open
R05 | Business | Regulatory and tax obligations (fiscal receipts, personal data, payment licensing) block launch or add scope | Venues must issue fiscal receipts; platform may be seen as handling funds; data protection law | 3 | 5 | 15 | Critical | Early advice from a local tax/legal adviser (Week 1); use licensed aggregator with direct settlement to venues; privacy notice and minimal data; clarify EFD/VFD handling and integrate or instruct venues. | Limit pilot to compliant venues; add fiscal integration as a priority story; delay launch rather than operate non-compliant. | Founder | Adviser feedback; venue questions on receipts | Open
R06 | Business | Low venue adoption or staff resistance | Perceived complexity, fear of losing tips, owner distrust of new tools | 3 | 4 | 12 | High | Co-design with pilot venues; show tip protection (guest can add tip); 30-minute training; waiter-first features; visible owner dashboard; free pilot period with success criteria. | Adjust workflow after feedback; on-site support for first 2 weekends; switch to higher-fit venues. | Founder | QR order share below 30% in week 2 | Open
R07 | Technical | Real-time layer degrades under peak load (Friday/Saturday nights) | Too many connections per node, Redis saturation, slow database queries | 2 | 4 | 8 | Medium | Load test before beta (9,000 connections); horizontal scaling; connection limits; efficient event payloads; DB indexes; autoscaling alarms. | Fallback to polling; scale out nodes; shed non-critical events. | Tech Lead | Event delivery p95 above 2 s; CPU > 70% | Open
R08 | Technical | Split race conditions create wrong shares or double claims | Concurrent edits by guests; late orders while splitting | 3 | 4 | 12 | High | Row lock on split; bill_version check; unique constraints; deterministic rounding; extensive Gherkin-based automated tests; property-based tests for rounding. | Waiter can void/reopen split; refund process for overpayment; audit log. | Backend Lead | Split recalculation conflicts (409) rate | Open
R09 | Operational | Fake or prank orders from people not at the table | Photographed or shared QR codes; no seat verification | 3 | 3 | 9 | Medium | Signed, rotatable QR; rate limits; waiter confirmation mode for new sessions at risk venues; unusual-order flags; table-level geofencing is NOT relied on (GPS unreliable indoors). | Waiter cancels order; rotate QR; block session. | Product Owner | Cancelled-by-waiter rate | Open
R10 | Technical | Duplicate or wrong payments (double tap, retries, wrong phone number) | Network retries, guest enters someone else’s number | 2 | 5 | 10 | High | Idempotency keys; one in-flight attempt per share (unique index); clear phone confirmation; amount shown on prompt; refund workflow documented with aggregator. | Manual refund via aggregator; flag needs_review; customer support script. | Backend Lead | Payments with needs_review flag | Open
R11 | Operational | Guests leave without paying (partial settlement) | Group members leave; reluctance to pay | 3 | 3 | 9 | Medium | Shares clearly visible to waiter; reminders; reassign unpaid share to others; cash fallback; encourage paying before leaving via prompts. | Waiter records outstanding amount; venue policy applies. | Product Owner | Unsettled tables at close | Open
R12 | Operational | Support overload on peak nights | New venues, training gaps, issues arriving simultaneously | 3 | 4 | 12 | High | Support rota for Fri/Sat; WhatsApp support line; in-app help; runbooks; staggered venue onboarding (max 3 per week). | Pause new onboarding; escalate to engineering on-call. | Support Lead | Open tickets older than 30 min on peak nights | Open
R13 | Business | Aggregator fees or pricing model erode margin | Transaction fees; low subscription price; free pilots | 3 | 4 | 12 | High | Model unit economics in Sprint 0; negotiate volume pricing; consider small fee pass-through or tiered plans; track cost per order. | Adjust pricing; renegotiate; change aggregator. | Founder | Gross margin per venue below target | Open
R14 | Technical | Security breach or data leak (phone numbers, payment data) | Weak access control, secrets leaks, dependency vulnerabilities | 2 | 5 | 10 | High | Encrypt MSISDN; RBAC and venue scoping tests; secret manager; dependency scanning; pen-test checklist; audit log; least-privilege cloud roles. | Incident response plan; notify affected parties as required; rotate keys. | Tech Lead | Security scan findings; anomalous access logs | Open
R15 | Business | Go-live collides with festive-season peak or a poorly timed launch | Late-year schedule pressure; venues too busy to train | 3 | 3 | 9 | Medium | Fix go-live window with venue input; soft launch to 2-3 venues first; change freeze on peak nights; training before peak week. | Delay beta by one to two weeks; run limited pilot on quieter days. | Founder | Venue availability for training | Open
R16 | Business | Small team capacity or key-person dependency | Few engineers; illness; context concentrated in one person | 3 | 4 | 12 | High | Documentation and runbooks; code reviews; pair on payments; keep scope flex (S4 as buffer); contractor option for peaks. | Descope Should/Could items; add contractor. | Founder | Velocity below 80% of plan for 2 sprints | Open
R17 | Business | Pricing resistance from venue owners | Perceived low value vs. existing methods | 3 | 4 | 12 | High | Pilot with measured outcomes (turnover, errors); tiered plans; month-to-month contracts; share ROI report after 4 weeks. | Adjust pricing or packaging; target higher-volume venues first. | Founder | Trial-to-paid conversion below 40% | Open
R18 | Technical | Device and browser fragmentation breaks UI on older phones | Old Android WebView, low memory devices | 3 | 3 | 9 | Medium | Device matrix with low-end Android; progressive enhancement; avoid heavy libraries; Sentry on real devices. | Hotfix and targeted polyfills; lite mode. | QA | Errors by browser/device in RUM | Open

## Heat Map
Risk heat map: number of risks by Probability (rows) and Impact (columns)
P \ I | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 2 | 1
3 | 0 | 0 | 4 | 6 | 2
2 | 0 | 0 | 0 | 1 | 2
1 | 0 | 0 | 0 | 0 | 0
Totals by rating
Critical | 5
High | 8
Medium | 5
Low | 0
Total | 18